## Sheet1
Session | Date | Tasks | Complete | Session Outcomes
1 | 2026-03-17 | Objective: Explain how Crazyflie sends data to Python | X | Commented every line and learned the blocks and what they do. Created some notes on higher level architecture. Still need to figure out specific code and some jargon but will get there.
1. Walk through the script
2. Identify connection setup, logging configuration, callback function
3. Understand how telemtry is requested, how data is received
2 | 2026-03-19 | Objective: Modify the telemetry script
1. Experiment: Log two values instead of one
3 | 2026-03-22 | Objective: First programmatic command
1. Script: connect, takeoff, hover 3 seconds, land
4 | 2026-03-24 | Objective: Position movement
1. Script: takeoff, move forward, move backward, land
5 | 2026-03-26 | Objective: Simple waypoint sequence
1. Script: takeoff, forward, left, back, right, land
6 | 2026-03-29 | Objective: Clean code + devlog
1. Document how commands work
2. Document how telemetry works
3. Document lessons learned
| 2026-03-31 | MARCH GOAL: connect → takeoff → simple movements → land